## Lab1
SN | Year | Net Yearly CashFlow (Rs.) | Cummulative CashFlow | Discount Factor (@ 6%) | Discounted CastFlow | Cummulative Discounted CashFlow
1 | 0 | -290000 | -290000 | 1 | -290000 | -290000
2 | 1 | 70000 | -220000 | 0.9434 | 66037.7358 | -223962.2642
3 | 2 | 70000 | -150000 | 0.89 | 62299.7508 | -161662.5133
4 | 3 | 70000 | -80000 | 0.83962 | 58773.3498 | -102889.1635
5 | 4 | 70000 | -10000 | 0.79209 | 55446.5564 | -47442.6071
6 | 5 | 70000 | 60000 | 0.74726 | 52308.0721 | 4865.465
No. of Year | 5 | Total Benefit :
350000
Total Investment / Cost :
290000
NetProfit: | 60000 | % |  |  |  |  | Net Profit = Total Benefit - Total Cost
Net ROI : | 20.6897 | % |  |  |  |  | ROI = NetProfilt / Total Investment * 100%
YearlyROI : | 4.1379 | % |  |  |  |  | Yearly ROI = Avarege Profit Per Year / Total Investment *100 %
PayBackPeriod: | 4.1429 | Year |  |  |  |  | PayBack Period = Year(Last Negative) + (Unrecovered Cash at start of the year/Yearly CashFlow)
NPV : | 4865.465 | [5 empty] | Discount Factor = 1/(1+6)^Year
Discounted PayBack Period: | 4.8556 | Year |  |  |  |  | Discounted CashFlow = DiscountFactor / CashFlow
IRR : | 6.615% | [5 empty] | NPV = Sum(Discounted CashFlow)
PW of Benefit : | 294865.465 | [5 empty] | PW of Benefit = Sum(Discounted CashFlow)
PW of Cost: | -290000 | [5 empty] | PW of Cost = Negative Cashflow
B-C Ratio : | 1.0168 | >1 means Project is Acceptable

## Lab3
| Activity | Duration | PerdayRate | TotalCost
| A | 2 | 300 | 600
| B | 3 | 400 | 1200
| C | 3 | 400 | 1200
| D | 2 | 200 | 400
| E | 3 | 100 | 300
ProgressMonitored(FieldReport) at day 7

## Lab3FieldReport
Field Report At The Enf Of Day 7
SN | Activity | Actual % Completed | IncurredCost
1 | A | 100 | 600
2 | B | 100 | 1400
3 | C | 33 | 500
4 | D | 50 | 200
5 | E | 0 | 0

## Lab3EVA Calculation
Activity | ACWP | BCWP | Required % Complete at Day 7 | BCWS
A | 600 | 600 | 100 | 600
B | 1400 | 1200 | 100 | 1200
C | 500 | 396 | 66 | 792
D | 200 | 200 | 100 | 400
E | 0 | 0 | 0 | 0
Sum | 2700 | 2396 |  | 2992
| CPI | BCWP/ACWP | 0.88741
| SPI | BCWP/BCWS | 0.8008
| CV | BCWP-ACWP | -304
| SV | BCWP-BCWS | -596
Conclusion:
The Project is Over Budget
The Project is Behind Schedule